## Bug Reports
SHIPMENT TRACKING SYSTEM — BUG REPORT LOG
Bug ID | Title | Module | API Endpoint | Steps to Reproduce | Expected Result | Actual Result | Severity | Status | Category | Reported By | Date Reported | Description / Impact
BUG-001 | Invalid status transition accepted (DELIVERED → CREATED) | Shipment Service | PUT /api/shipments/{id}/status | 1. Create shipment 2. Update status to IN_TRANSIT 3. Update to DELIVERED 4. Update back to CREATED | 400 Bad Request — invalid status transition not allowed | 201 OK — status reverted to CREATED (incorrect) | High | Open | Business Logic | Digvijaysing Rajput | 2024-11-10 | No validation on backward status transitions. Shipments can be incorrectly moved to earlier states after delivery.
BUG-002 | Redis cache not invalidated on shipment status update | Shipment Service | GET /api/shipments/{id} | 1. GET shipment/{id} — cache populated 2. PUT status update 3. GET shipment/{id} again | Updated status returned immediately from fresh data | Old (stale) status returned from Redis cache — cache not invalidated on update | High | Open | Caching | Digvijaysing Rajput | 2024-11-11 | Cache invalidation missing in status update flow. Users see incorrect shipment status after update.
BUG-003 | Rate limiter returns 500 instead of 429 on limit exceeded | API Gateway | Any endpoint (>1000 req/s per IP) | 1. Send 1100 requests/sec from single IP 2. Observe responses beyond limit | 429 Too Many Requests with Retry-After header | 500 Internal Server Error returned; no rate limit message | Medium | Open | Rate Limiting | Digvijaysing Rajput | 2024-11-12 | Rate limiter error handling misconfigured. Should return 429, not 500. Impacts client error handling.
BUG-004 | AI Prediction service returns null ETA for long-distance shipments | AI Prediction Service | POST /api/predictions/predict | 1. Send predict request with distanceKm = 5000 2. Check ETA value in response | Valid ETA value calculated and returned | Response contains eta: null — calculation fails silently for large distances | Medium | In Progress | Calculation | Digvijaysing Rajput | 2024-11-13 | ETA formula possibly overflows or hits edge case for distances > 4000km. Needs boundary value fix.
BUG-005 | Notification service crashes on malformed Kafka message | Notification Service | Kafka topic: shipment-events | 1. Publish malformed JSON to shipment-events topic 2. Monitor notification-service logs | Error logged gracefully; service continues running | Notification service pod crashes; requires manual restart | High | Open | Error Handling | Digvijaysing Rajput | 2024-11-14 | Missing try-catch around Kafka message deserialization. Single bad message takes down service.
BUG-006 | Tracking history returns events in wrong order | Tracking Service | GET /api/tracking/{id}/history | 1. Create shipment 2. Update status 3 times with delays 3. Fetch /tracking/{id}/history | Events returned in ascending chronological order (oldest first) | Events returned in random/insertion order — not sorted by timestamp | Medium | Open | Data Integrity | Digvijaysing Rajput | 2024-11-15 | Missing ORDER BY timestamp in tracking history query. Misleads users about shipment journey.
BUG-007 | User enumeration via login error message | User Service | POST /api/users/login | 1. Login with unregistered email 2. Login with registered email + wrong password 3. Compare error messages | Same generic error message for both scenarios | Different messages: 'User not found' vs 'Wrong password' — reveals registered emails | Medium | Open | Security | Digvijaysing Rajput | 2024-11-16 | Distinct error messages allow attackers to enumerate valid user emails. Should return same generic message.
BUG-008 | Pagination returns duplicate records on page boundary | Shipment Service | GET /api/shipments?page=1&size=10 | 1. Create 21 shipments 2. Fetch page=1&size=10 3. Fetch page=2&size=10 | 20 unique records across 2 pages, 1 on page 3 | Record at page boundary appears on both page 1 and page 2 | Low | Open | Pagination | Digvijaysing Rajput | 2024-11-17 | Off-by-one in pagination offset calculation. Duplicates confuse UI and reports.